## Tasks and Schedule
| Task | Who | Complete by 6/13/2013 | Completion date
1 | Identify first and subsequent sites for data collection. Meet with homeowners and examine overall suitability. | Dan | Talk to homeowners | 2013-07-12
2 | Evaluate and identify best option for system integration (RasberyPI, Labjack, Campbell, laptop, or ???) | Justin/Jon | Fairly firm decision on system | 2013-07-12
3 | Purchase met station and configure for data collection | Jeffrey | Decision on type needed | 2013-07-12
4 | Operate DustTrak at Duwamish PSCAA site for one week and compare results. | Jeffrey | none | 2013-07-01
5 | Calibrate CO2 sensor and evaluate data storage | Sofya | Prelim cal | 2013-07-01
6 | Evaluate and configure webcam for train identification. ID methodology to get train speed from photos. ID method for picture data storage. | Greg | Id best options | 2013-07-05
7 | Test CO2 response/detectability at track. Conduct prelim tests on CO2 and PM correlation. | Sofya/Jeffrey |  | 2013-07-05
8 | Choose data interval for CO2 and PM measurements | Sofya/Jeffrey/Dan |  | 2013-07-05
9 | Build prototype, integrate system and test at the track. | All |  | 2013-07-12
10 | Integrate system (PM, CO2, met and webcam). Arrange power and data download configuration. Install into water proof box. | All |  | 2013-07-12
11 | Test data collection at Puget Sound location. Evaluate data to determine if goals can be met. | All |  | 2013-07-12
12 | Start data collection at Puget Sound location | All |  | 2013-07-15
13 | Start data analysis immediately to examine suitability for project goals. Modify as needed. | All
14 | Develop algorithms to automate data processing as much as possible (train id, speed, CO2/PM relationships, etc). | All
15 | Start data collection at CRG location | All |  | 2013-08-15

## Project Goals
| Goals | Notes
1 | Identify possible sites in the Puget Sound with highest exposure to DPM from trains. This will likely be urban areas where trains are moving relatively slowly and with relatively low wind speeds.
2 | Identify site with highest exposure to coal dust from trains. This site will be in the CRG where trains are moving at high speed.
3 | Quantify exposure (ug/m3) in four binned sizes at each site.
4 | Use relationship between CO2 and PM1 to calculate emission factors for DPM.
5 | Use relationship between CO2 and binned PM to calculate "dust emission factor" for coal dust as a function of wind speed.

## Potential sites
1 | Liz Talley | 3220 NW Esplanade | Seattle | carlantapp.blogspot.com | 206-235-6271
3 | Paul Cavanhaugh | 2302 NW Blue Ridge Drive | Seattle | cavanaugh.paul@outlook.com
| Janice Keller | 10301 Bedford Ct NW (Blue Ridge) | Seattle | jankell@earthlink.net
2 | Bill Demetre | 18922 Sound View Place | Edmonds | bdeme8@gmail.com
| Ben Broesamle | 4051 Gilman Ave West | Seattle | bbroesamle@gmail.com
| Elizabeth Hines | 608 Blvd St | Bellingham | northstardieselmarine@yahoo.com
| Steve Sanger | 600 South State St./Riptide Condos | Bellingham | stevelsanger@hotmail.com
| Dick Deal | 19425-27th Ave | Shoreline/Richmond Beach | ddeal@shorelinewa.gov
| Richard Gammon | 20240 Richmond Beach Drive NW | Seattle | gammon@uw.edu
| Jeff Thompson | 3443 Thorndyke Avenue West | Seattle | jeff@thefreeholdgroup.com