## Slide 1: Elements of Project Planning
Divide project into tasks, tasks into subtasks, subtasks into ...
Estimate duration of each task, subtask, ...
Estimate resource requirements for each task, subtask, ...(budget, personnel, facilities)
Identify precedence relations among tasks

## Slide 2: Benefits of Project Planning
Communications tool
Resource allocation
Benchmarking

## Slide 3: Keeping Engineers Busy with Multiple Projects
this image is not available yet
Fig. 7.1

## Slide 4: Stages of Engineering Design Projects
Enthusiasm
Disillusionment
Panic
Search for the guilty
Punishment for the innocent
Praise and honors for the non-participants

## Slide 5: Project Planning Tools
Gantt Chart
Critical Path Method (CPM)
Program Evaluation and Review Technique (PERT)
Variations and combinations of the above
Many available software packages contain these tools

## Slide 6: Gantt Chart for Automobile Bumper Project
Fig. 7.2

## Slide 7: Enhanced Gantt Chart for Automobile Bumper Project
Fig. 7.3

## Slide 8: Keeping Track of Project Progress on a Gantt Chart
Fig. 7.4

## Slide 9: Typical Electric Substation
Fig. E7.3.1(a)

## Slide 10: Tasks for Designing and Building an Electric Substation
Table E 7.3.1

## Slide 11: Gantt Chart for Substation Design and Construction
Fig. E7.3.1(b)

## Slide 12: Critical Path Method (CPM)
Uses a network flow diagram to depict the precedence relations among activities (tasks)
Elements of diagram are directed line segments and nodes
Facilitates identification of activities whose timely completion are “critical” to timely completion of the project

## Slide 13: CPM Notation and Conventions
An activity is an ongoing effort on a project task (directed line segment).
Every activity has an initiating event and a closing event (nodes).
Events consume no time. Their primary role in CPM diagrams is to separate activities.
Consecutive activities must be separated by events.
Fig. 7.6

## Slide 14: CPM Notation and Conventions (cont.)
No pair of events can be directly connected by more than one activity with no intervening events. If an activity R must immediately precede S and T, the relationship is depicted as follows
Fig. 7.7(a)
If activities R and S must both immediately precede T, the relationship is depicted as follows
Fig. 7.7(b)
All networks must begin with a single Start event and end with a single Finish event.

## Slide 15: Dummy Activities
Sometimes precedence relationships require the use of a dummy activity (depicted by a dashed line) to indicate the appropriate relationships. Dummy activities do not take up any time.
Dummy activity is needed to correctly depict that P and Q must precede S, and P must precede R.
Dummy activity needed when several activities have same Start and End events. Activities R and S share the same Start and End events.
Fig. 7.10
Dummy activities should be be included only when needed to display the precedence relation.

## Slide 16: Precedence Relations for Several Activities of Bumper Project
Table 7.2
Activity | Preceded by
Design bracket | 
Build bracket | Design bracket
Build bumper | 
Drill holes in bumper | Build bumper, Design bracket

## Slide 17: Using Dummy Activity for Bumper Project
Fig. 7.8

## Slide 18: Multiple Dummy Activities
A precedes D
A and B precede E
B and C precede F
Fig. 7.9

## Slide 19: Project Activities and their Precedence Relations
Table 7.1
Activity | Duration | Preceded by
A | 3 | 
B | 3 | A
C | 4 | 
D | 1 | C
E | 3 | B, D
F | 2 | A, B, D
G | 2 | C, F
H | 4 | G
I | 1 | C
J | 3 | E, G
K | 5 | F, H, I

## Slide 20: Constructing a Network Diagram
Fig. 7.12
Fig. 7.11

## Slide 21: Example of Constructing a Network Diagram
Table E7.4.1
Fig. E7.4.1
Activity | Preceded by
A | 
B | 
C | 
D | A,B
E | C
F | A
G | D, E, F
H | C
I | H
J | D, E
K | I, J
L | G
M | L, K

## Slide 22
Another Example of Constructing a Network Diagram*

## Slide 23: The Critical Path
The critical path is the path of activities from the start event to the finish event for which delay in any activity along that path will delay the project finish.
For projects with a small number of alternative paths, the critical path can be most efficiently identified by finding the longest of the alternative paths.

## Slide 24: Alternative Paths and their Length
For the project depicted in Fig. 7.12
Table 7.3
Thus, A-B-F-G-H-K is the critical path

## Slide 25: Critical Path Depicted on Network Diagram
Fig. 7.13

## Slide 26: Example Problem of Finding the Critical Path*

## Slide 27: Alternate Method for Determining Critical Path
This approach is more efficient for larger networks
  Use forward sweep to find earliest start (ES) for each activity
  Use backward sweep to find latest start (LS) for each activity
  Calculate total float (TF) for each activity
    TF = LS - ES
  Critical Path consists of Activities with TF = 0

## Slide 28: Earliest Start*
Earliest Start (ES) is the earliest time an activity can start. It is found by tracing forward (from tail to head of each activity arrow) from the project Start event to the tail of the selected activity. When several paths are possible, use the longest path as determined by the sum of the activity durations on that path.
For activity F, ES = 9

## Slide 29: Project Duration*
Continue until we have ES for all activities that terminate in the project Finish event. When duration of each of those activities are added to their respective ES times, the largest of the resulting sums is defined as the Project Duration.
For activity H, ES=20
Project Duration =20+4=24

## Slide 30: Latest Start*
Latest Start (LS) is the latest time an activity can start and still have the project completed within the Project Duration time.
LS is found by tracing backwards (from head to tail of each activity) from the project Finish event to the tail of selected activity. Make sure you reach the tail of the selected activity via the head of that activity. When several paths are possible, use the longest path as determined by the sum of the activity durations on that path. The Project Duration minus the length of this longest path is the LS for the selected activity.
For activity A, LS=24-24=0

## Slide 31: Total Float
Total Float for each activity is the difference between the latest start and the earliest start.
TF = LS - ES
The activities for which TF=0 define the critical path.

## Slide 32: Summary of Total Float Calculations*
Critical Path consists of A-D-F-G-H

## Slide 33: Total Float Calculations
Table 7.4
For project shown in Fig. 7.12

## Slide 34: Example of Critical Path Determination
Fig. E7.4.2(a)

## Slide 35: Summary of Example Float Calculations
Table E7.4.2

## Slide 36: Critical Path for Example Problem
Fig. E7.4.2(b)

## Slide 37: Program Evaluation and Review Technique (PERT)
Based on Critical Path Method
Replaces single estimate of activity duration by a probability distribution
Allows estimate of probability of completing project by a specified time

## Slide 38: Typical Beta Distributions for Activity Durations
to-optimistic estimate; the shortest time within which this activity can be completed assuming everything goes right. This is the left terminus of the pdf.
tm-the most likely time required to complete the activity. This is the mode of the pdf.
tp- pessimistic estimate; the longest time it will take this activity to be completed assuming everything goes wrong. This is the right terminus of the pdf.
Fig. 7.14

## Slide 39: Network Diagram for PERT Example Problem
Fig. 7.15

## Slide 40: PERT Procedure
Calculate the expected duration te (mean) of each activity
Calculate the variance 2 of each activity
Use te to determine the expected project duration Te and identify the critical path

## Slide 41: Determination of Critical Path for PERT Example Calculation
Table 7.5

## Slide 42: PERT Critical Path
Fig. 7.16

## Slide 43: Probability of Completing Project by Specified time Ts
Calculate the variance of the project duration as the sum of the variances of the activities on the critical path
Use the standard normal variable z to find the probability of completing the project in a specified time Ts
For Ts=20
From Table 5.1
Pr (z < -0.57) = 0.285

## Slide 44: Space Station PERT Problem
Fig. E7.5.1(a)
This image is not yet available

## Slide 45: Activities for Space Station PERT Problem
Table E7.5.1(a)

## Slide 46: PERT Diagram for Space Station Project
Fig. E7.5.1(b)

## Slide 47: Summary of PERT Calculations for Space Station Project
Table E7.5.1(b)

## Slide 48: Another PERT Example Problem*

## Slide 49: Probability of Completing Project by Specified time Ts*
Calculate the variance of the project duration as the sum of the variances of the activities on the critical path
Use the standard normal variable z to find the probability of completing the project in a specified time Ts
For Ts=30
From Table 5.1
Pr (z < 1.48) = 1 - Pr (z < -1.48) = 1 - 0.067 = 0.932

## Slide 50: CPM Diagram with Nodes Numbered
Fig. 7.17

## Slide 51: Calendarized Version of Network Diagram
Fig. 7.18

## Slide 52: Activity on Node Network Diagram
Fig. 7.19

## Slide 53: Refined Activity on Node Network Diagram
Fig. 7.20